## Group BPMB
Group BPMB - Innovation & Digital Initiatives List
Initiatives ID | Initiative Name | Status (Completed / In Progress / Not Started) | Description of Initiative | Requester | PIC | Stakeholder | Target Start | Actual Start | Target End | Actual End | Complexity (High/Medium/Low) | Prioritisation (High/Medium/Low) | Budget | Progress | Group | Remarks (Description of Status/RAID)
IDG001 | Asset Tokenization | In Progress | Enable BPMB asset tokenization. | GCEO Office | Hasanal, Eskandar | Group Operation, Corporate Banking | 2026-01-01 | 2026-01-01 | 2026-12-01 |  | High | High | 500000 |  | Group BPMB | 1. NDA signed, high level requirement defined, motioning with POC with D2G and KLDX. 2. Business case paper to be presented in EXCO July 2026.
IDG002 | AI Infrastructure | In Progress | To establish AI infrastructure for AI R&D and deployment, including a GPU-ready on-premises AI Lab. | ID | Azil, Borhan | Technology Operation, GRM | 2026-01-01 | 2026-01-01 | 2026-12-01 |  | High | High | 800000 |  | Group BPMB | 1. RFI stage to identify potential provider and solutions for the GaaS. 2. Discovery exercise with TM Credence to expand current SME IaaS for AI Data Lake and GaaS. 3. Exploring AI industry players such as AliBaba, CloudWise for AI tools/platform.
IDG003 | BPMB Group AI Strategy & Roadmap | In Progress | To formulate a holistic three-year AI strategy and roadmap for BPMB Group. | GIT | Eskandar, Najib | EA, Technology Operation, IT Strategy Governance, GRM | 2026-01-01 | 2026-01-01 | 2026-12-01 |  | High | High |  |  | Group BPMB | 1. To retable the revised and refined AI Strategy & Roadmap in September GMITC together with the Cloud Strategy Roadmap.
IDG004 | Digital Awareness | Not Started | To elevate digital literacy across BPMB Group through technology updates, awareness sessions, and digital initiatives (e.g., AI Hackathon and Digital Day). | GIT | Lukman, Najib | GIT | 2026-08-01 | 2026-08-01 | 2026-12-01 |  | Medium | Medium | 100000 |  | Group BPMB | Planning Stage
IDG005 | ELSA for BPMB Group | In Progress | To scale the ELSA platform across BPMB Group to optimise operations. | GCEO Office | Azil | GIT, Corporate Banking, PLC, DANA, and others | 2026-01-01 | 2026-01-01 | 2026-12-01 |  | High | High | 2000000 |  | Group BPMB | 1. Current state information gathering on BPMB Group As-Is customer onboarding process and channels.
IDG006 | AI Policy & Guidelines | In Progress | To define and standardise AI guardrails for AI implementation and usage across BPMB Group. | GRM | Najib, Husainy | IT Strategy Governance, GRM, ID | 2026-05-01 | 2026-05-01 | 2026-10-01 |  | High | High |  |  | Group BPMB | 1. Alignment with BPMB Group CISO on the AI standard framework (prepared by EY) shared by AICB.
IDG007 | AI Community of Practice (AI COP) | In Progress | To establish an AI COP and learn from or share AI-related knowledge with members from various industries. | GIT | Hairil, Eskandar | AI Industry players, ABC | 2026-07-01 | 2026-07-01 |  |  | Medium | Medium |  |  | Group BPMB | 1. First AI Business Chamber (ABC) conducted in early July 2026.
IDG008 | PINTAR | In Progress | To scale PINTAR adoption across BPMB Group through the initial PGP Harmonisation use case (PINTAR.PGP). | GIT | Lukman | ID | 2026-05-01 | 2026-05-01 | 2026-12-01 |  | Medium | Medium |  |  | Group BPMB | 1. Transition handover to DevOps team to be conducted by end of July 2026. 2. Market Risk to become PINTAR.PGP champion to accelerate adoption.
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Function Owner
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on business perspectives

## BPMB
2026 BPMB - Innovation & Digital Initiatives List
Initiatives ID | Initiative Name | Status (Completed / In Progress / Not Started) | Description of Initiative | Requester | PIC | Stakeholder | Target Start | Actual Start | Target End | Actual End | Complexity (High/Medium/Low) | Prioritisation (High/Medium/Low) | Budget | Progress | Group | Remarks (Description of Status/RAID)
IDB001 | AppRef Enhancement | Completed | Enhances Reference Number System dashboard with supervisor approvals and terminology | Coverage | Faizan | Coverage | 2026-01-01 | 2025-12-01 | 2026-03-01 | 2026-01-01 | Low | Low | 100000 | 100% | BPMB
IDB002 | Template Report for Commercial Banking Listing | Completed | Automates preparation of Commercial Banking reports aligned with BNM guidelines | Credit Admin | Faizan | Credit Admin | 2026-01-01 | 2026-01-01 | 2026-03-01 | 2026-02-01 | Low | Low |  | 100% | BPMB
IDB003 | Enhancement Service Requisition | Completed | Enhances handling of failed requests and missing notifications in Iron Mountain service | Credit Admin | Husnina | Credit Admin | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-03-01 | Low | Low |  | 100% | BPMB
IDB004 | Corporate Hospitality & Entertainment (CHE) Form | In Progress | To digitalize Corporate Hospitality & Entertainment (CHE) Form for GCEO or CFO approval | Compliance | Izzat, Faizan | Compliance | 2026-01-01 | 2025-12-01 | 2026-03-01 | 2026-03-01 | Medium | Medium |  | 30% | BPMB
IDB005 | ELMS Repayment Schedule / Monthly Summary of Payment Schedule | In Progress | Format and calculate ELMS repayment schedule values | Credit Admin | Irfan | Credit Admin | 2026-02-01 |  | 2026-06-01 |  | Low | Low |  |  | BPMB
IDB006 | CCRIS DQR1 Report Automation | In Progress | To automate CCRIS DQR 1 for BNM monthly submission from ELMS | Credit Admin | Irfan | Credit Admin | 2026-02-01 |  | 2026-06-01 |  | High | High |  |  | BPMB
IDB007 | Zakat Management Database & Reporting | In Progress | Dashboard to analyse contributions to zakat projects | Group Shariah Management | Irfan | Group Shariah Management | 2026-06-01 | 2026-04-01 | 2026-09-01 |  | Medium | Medium |  |  | BPMB
IDB008 | Staff Loan Tracking - Log Platform | Not Started | Automate extracting payment schedules from HRMS into a data warehouse | HR | Irfan, Husnina | HR | 2026-06-01 |  | 2026-09-01 |  | High | High |  |  | BPMB
IDB009 | Staff Loan Tracking - CCRIS SDIS Submission | Not Started | Automation to keep track of the logs of staff loan payment history | HR | Irfan, Husnina | HR | 2026-06-01 |  | 2026-09-01 |  | High | High |  |  | BPMB
IDB010 | Negative Listing Searches | Not Started | Automate the negative listing search process of identifying a hit against beneficiaries | Credit Admin | Irfan | Credit Admin | 2026-09-01 |  | 2026-12-01 |  | High | High |  |  | BPMB
IDB011 | Details Statement of Account (Enhancement) | In Progress | Statement of Account enhancement: download statements for impaired active accounts | Credit Admin | Irfan | Credit Admin | 2026-02-01 |  | 2026-06-01 |  | Low | Low |  |  | BPMB
IDB012 | Daily Disbursement & Payment Report | In Progress | Automate generating detail movement/listing of each Disbursement & Collection on daily basis | Credit Admin | Husnina | Credit Admin | 2026-01-01 | 2026-01-01 | 2026-06-01 |  | Medium | Medium |  | 80% | BPMB
IDB013 | Disbursement Documentation Filling | In Progress | Automate the upload and transfer of disbursement documents between sharepoint sites | Credit Admin | Husnina | Credit Admin | 2026-06-01 | 2026-03-01 | 2026-09-01 |  | Medium | Medium |  |  | BPMB
IDB014 | Payment Schedule Enhancement | Completed | Payment Schedule enhancement: change how certain values are calculated | Credit Admin | Husnina | Credit Admin | 2026-02-01 | 2026-03-01 | 2026-06-01 | 2026-06-01 | Low | Low |  | 100% | BPMB
IDB015 | Auto-Generated Email Reminder | Not Started | Send email reminders to RMs and BPMB clients based on deal status | Corporate Banking | Irfan | Corporate Banking | 2026-06-01 |  | 2026-09-01 |  | Low | Low |  |  | BPMB
IDB016 | Elysian Recoveries Script Enhancement | In Progress | ELMS Elysian extractions enhancement: change filtering for account status | Finance | Irfan | Finance | 2026-02-01 |  | 2026-06-01 |  | Low | Low |  |  | BPMB
IDB017 | Customer Screening Automation LEA | Not Started | Automate screening of customer data in ELMS against list provided by law enforcement agencies | Compliance | Irfan | Compliance | 2026-09-01 |  | 2026-12-01 |  | High | High |  |  | BPMB
IDB018 | PINTAR.Procurement | Completed | AI Assistant that enables users to ask questions in plain language and instantly receive accurate, relevant answers drawn from a curated knowledge base of BPMB procurement policy documents | Strategic Procurement | Irfan, Husnina | Strategic Procurement | 2025-11-01 | 2025-11-01 | 2026-03-01 | 2026-03-01 | Medium | Medium |  |  | BPMB
IDB019 | PINTAR.MarketRisk | Not Started | AI Assistant to assist the Market Risk team by retrieving relevant answers from Market Risk policy documents | Market Risk | Irfan, Husnina | Market Risk | 2026-06-01 |  | 2026-09-01 |  | Medium | Medium |  |  | BPMB
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Function Owner
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on business perspectives

## oriBPMB (hidden)
2026 BPMB Process Initiatives – Completed and Planned
No | Initiative Name | Status (Completed / Planned) | Description of Initiative | Owner / PIC | Stakeholder | Expected Impact (Business / Cost / Efficiency) | Complexity (High/Medium/Low) | Prioritisation (High/Medium/Low) | Timeline (Start Date & End Date) | Remarks | Budget
1 | AppRef Enhancement | Completed | Enhances Reference Number System dashboard with supervisor approvals and terminology | Faizan | Coverage |  | Low |  | Q1 2026
2 | Template Report for Commercial Banking Listing | Completed | Automates preparation of Commercial Banking reports aligned with BNM guidelines | Faizan | Credit Admin |  | Low |  | Q1 2026
3 | Enhancement Service Requisition | Completed | Enhances handling of failed requests and missing notifications in Iron Mountain service | Husnina | Credit Admin |  | Low |  | Q1 2026
4 | Corporate Hospitality & Entertainment (CHE) Form | Completed | To digitalize Corporate Hospitality & Entertainment (CHE) Form for GCEO or CFO approval | Izzat Faizan | Compliance |  | Medium |  | Q1 2026
5 | ELMS Repayment Schedule / Monthly Summary of Payment Schedule | Planned | Format and calculate ELMS repayment schedule values | Irfan | Credit Admin |  | Low |  | Q2 2026
6 | CCRIS DQR1 Report Automation | Planned | To automate CCRIS DQR 1 for BNM monthly submission from ELMS | Irfan | Credit Admin |  | High |  | Q2 2026
7 | Zakat Management Database & Reporting | Planned | Dashboard to analyse contributions to zakat projects | Irfan | Group Shariah Management |  | Medium |  | Q3 2026
8 | Staff Loan Tracking - Log Platform | Planned | Automate extracting payment schedules from HRMS into a data warehouse | Irfan Husnina | HR |  | High |  | Q3 2026
9 | Staff Loan Tracking - CCRIS SDIS Submission | Planned | Automation to keep track of the logs of staff loan payment history | Irfan Husnina | HR |  | High |  | Q3 2026
10 | Negative Listing Searches | Planned | Automate the negative listing search process of identifying a hit against beneficiaries | Irfan | Credit Admin |  | High |  | Q4 2026
11 | Details Statement of Account (Enhancement) | Planned | Statement of Account enhancement: download statements for impaired active accounts | Irfan | Credit Admin |  | Low |  | Q2 2026
12 | Daily Disbursement & Payment Report | Planned | Automate generating detail movement/listing of each Disbursement & Collection on daily basis | Husnina | Credit Admin |  | Medium |  | Q2 2026
13 | Disbursement Documentation Filling | Planned | Automate the upload and transfer of disbursement documents between sharepoint sites | Husnina | Credit Admin |  | Medium |  | Q3 2026
14 | Payment Schedule Enhancement | Completed | Payment Schedule enhancement: change how certain values are calculated | Husnina | Credit Admin |  | Low |  | Q2 2026
15 | Auto-Generated Email Reminder | Planned | Send email reminders to RMs and BPMB clients based on deal status | Irfan | Corporate Banking |  | Low |  | Q3 2026
16 | Elysian Recoveries Script Enhancement | Planned | ELMS Elysian extractions enhancement: change filtering for account status | Irfan | Finance |  | Low |  | Q2 2026
17 | Customer Screening Automation LEA | Planned | Automate screening of customer data in ELMS against list provided by law enforcement agencies | Irfan | Compliance |  | High |  | Q4 2026
18 | PINTAR.Procurement | Completed | AI Assistant that enables users to ask questions in plain language and instantly receive accurate, relevant answers drawn from a curated knowledge base of BPMB procurement policy documents | Irfan Husnina | Strategic Procurement | Med | Medium |  | Q1 2026
19 | PINTAR.MarketRisk | Planned | AI Assistant to assist the Market Risk team by retrieving relevant answers from Market Risk policy documents | Irfan Husnina | Market Risk | Med | Medium |  | Q3 2026

## EXIM
2026 EXIM - Innovation & Digital Initiatives List
Initiatives ID | Initiative Name | Status (Completed / In Progress / Not Started) | Description of Initiative | Requester | PIC | Stakeholder | Target Start | Actual Start | Target End | Actual End | Complexity (High/Medium/Low) | Prioritisation (High/Medium/Low) | Budget | Progress | Group | Remarks (Description of Status/RAID)
IDE001 | ECR Interface (Disbursement/Drawdown) to swift | In Progress | to generate MX swift format file for disbursement/drowdown transactions and interface to the Swift Saa System | Finance | Rozaimi | Finance | 2026-09-01 |  | 2026-12-01 |  | Medium | Medium |  |  | EXIM
IDE002 | MIS & ECITS Enhancement - Centralized CIF | In Progress | to Centralize CIF module at MIS system | Finance & Compliance | Afif | Finance & Compliance | 2026-09-01 |  | 2026-12-01 |  | Medium | Medium |  |  | EXIM
IDE003 | EFMS - Purchase New AA requirement | Completed | New Approval Authority requirement in EFMS system | Procurement | Afif | Procurement | 2026-03-01 |  | 2026-06-01 |  | Medium | Medium |  |  | EXIM
IDE004 | MIS - Annual Review Reminder Enhancement | Completed | Annual Review Reminder Enhancement | Banking | Alifah | Banking | 2026-03-01 |  | 2026-06-01 |  | Medium | Medium |  |  | EXIM
IDE005 | JasperReport- Compliance ECR to BNM | Completed | New Report request by Comliance Department | COD | Alifah, Syahid | COD | 2026-03-01 |  | 2026-06-01 |  | Medium | Medium |  |  | EXIM
IDE006 | MIS - BNM exchange rate integration | Completed | Auto pickup BNM rate through BNM Open Api | Finance | Rozaimi | Finance | 2026-03-01 |  | 2026-06-01 |  | Medium | Medium |  |  | EXIM
IDE007 | Copilot Studio Agent (Ex-cellence) | In Progress | An AI Assistant for ITD team in decision making, instruction and documentation | ITD | Syahid | ITD | 2026-06-01 |  | 2026-09-01 |  | Medium | Medium |  |  | EXIM
IDE008 | Technology Refresh :MS SQL upgrade for ECITS system | In Progress | MS SQL upgrade for ECITS system (Support) | IT/COD | Afif | IT/COD | 2026-06-01 |  | 2026-09-01 |  | High | High |  |  | EXIM
IDE009 | Technology Refresh :MS SQL upgrade for ECR system | In Progress | MS SQL upgrade for ECR system (Support) | IT/COD | Rozaimi | IT/COD | 2026-06-01 |  | 2026-09-01 |  | High | High |  |  | EXIM
IDE010 | Power BI - Monthly Reporting of Trade Finance (EXCO - other matter) | Completed | Dashboard & Reporting | COD | Syahid | COD | 2026-03-01 |  | 2026-06-01 |  | Medium | Medium |  |  | EXIM
IDE011 | Power BI - Monthly Reporting of Non Trade Finance (EXCO - other matter) | Completed | Dashboard & Reporting | COD | Syahid | COD | 2026-03-01 |  | 2026-06-01 |  | Medium | Medium |  |  | EXIM
IDE012 | EFMS - Digitilise Pantry Request Form | In Progress | Digitilise Pantry Request Form (WorkFlow) | Admin | Afif | Admin | 2026-06-01 |  | 2026-09-01 |  | Medium | Medium |  |  | EXIM
IDE013 | efms - Digitilise Stationary Request Form | Completed | Digitilise Stationary Request Form (WorkFlow) | Admin | Afif | Admin | 2026-03-01 |  | 2026-06-01 |  | Medium | Medium |  |  | EXIM
IDE014 | ECITS - Enhancement : Apprroval Process Digitilization | Not Started | Digitilise Approval Process in System | Banking | Awang | Banking | 2026-09-01 |  | 2026-12-01 |  | High | High |  |  | EXIM
IDE015 | MIS - Automation for Credit Limit – Connected Party Transaction | Not Started | Reporting | Risk | Afif | Risk | 2026-03-01 |  | 2026-06-01 |  | Medium | Medium |  |  | EXIM
IDE016 | MIS - Trade Customer Monthly Statement | Not Started | Automate Trade Monthly Statement | COD | Alifah | COD |  |  |  |  | High | High |  |  | EXIM
IDE017 | ECR - new reminder redemption report sent to email for ECR bank on maturity date | Completed | Automate Submit reminder to ECR bank on the Bills Maturity | COD | Rozaimi | COD | 2026-06-01 |  | 2026-09-01 |  | High | High |  |  | EXIM
IDE018 | In-House Microsoft 365 Compliant Passwordless Login | Not Started | Enable sso login with device's pin code | IT | Rozaimi | IT |  |  |  |  | Medium | Medium |  |  | EXIM
IDE019 | Python - CCRIS Template Download | Completed |  | Finance | Syahid | Finance |  |  |  |  | Medium | Medium |  |  | EXIM
IDE020 | ECITS Enhancement- Go Export Subsidies | Not Started | New requirment to enhance policy premium with Go Export Subsidies | Banking | Awang | Banking | 2026-06-01 |  | 2026-09-01 |  | High | High |  |  | EXIM
IDE021 | EFMS - Document Box Tracker | Not Started | Digitilise Admin Document Movement (Workflow) | Admin | Awang | Admin | 2026-09-01 |  | 2026-12-01 |  | Medium | Medium |  |  | EXIM
IDE022 | Power BI - Business Performance | Not Started | Dashboard & Reporting | Banking | Syahid | Banking | 2026-06-01 |  | 2026-09-01 |  | Medium | Medium |  |  | EXIM
IDE023 | Power BI - Product Profitability | Not Started | Dashboard & Reporting | Product | Syahid | Product |  |  |  |  | Medium | Medium |  |  | EXIM
IDE024 | Centralized CIF : ECITS integration with Core Banking | Not Started | to Centralize CIF module at Core Banking system | ALL | Afif | ALL | 2026-09-01 |  | 2026-12-01 |  | High | High |  |  | EXIM
IDE025 | Centralized CIF : ECR integration with Core Banking | Not Started | to Centralize CIF module at Core Banking system | ALL | Rozaimi | ALL | 2026-09-01 |  | 2026-12-01 |  | High | High |  |  | EXIM
IDE026 | Machine Learning Application (Regression) | Not Started | Mathematical modelling in prediction requirement for the desired outcome | ITD | Syahid | ITD | 2026-09-01 |  | 2026-12-01 |  | Medium | Medium |  |  | EXIM
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Function Owner
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on business perspectives

## oriEXIM (hidden)
2026 EXIM Business Process Initiatives – Completed and Planned
No | Initiative Name | Status (Completed / Planned) | Description of Initiative | Owner / PIC | Stakeholder | Expected Impact (Business / Cost / Efficiency) | Complexity (High/Medium/Low) | Prioritisation (High/Medium/Low) | Timeline (Start Date & End Date) | Remarks | Budget
1 | ECR Interface (Disbursement/Drawdown) to swift | Planned | to generate MX swift format file for disbursement/drowdown transactions and interface to the Swift Saa System | Rozaimi | Finance | Efficiency | Medium |  | Q4 2026
2 | MIS & ECITS Enhancement - Centralized CIF | Planned | to Centralize CIF module at MIS system | Afif | Finance & Compliance | Business | Medium |  | Q4 2026
3 | EFMS - Purchase New AA requirement | Completed | New Approval Authority requirement in EFMS system | Afif | Procurement | Business | Medium |  | Q2 2026
4 | MIS - Annual Review Reminder Enhancement | Completed | Annual Review Reminder Enhancement | Alifah | Banking | Business | Medium |  | Q2 2026
5 | JasperReport- Compliance ECR to BNM | Completed | New Report request by Comliance Department | Alifah & Syahid | COD | Business | Medium |  | Q2 2026
6 | MIS - BNM exchange rate integration | Completed | Auto pickup BNM rate through BNM Open Api | Rozaimi | Finance | Efficiency | Medium |  | Q2 2026
7 | Copilot Studio Agent (Ex-cellence) | Planned | An AI Assistant for ITD team in decision making, instruction and documentation | Syahid | ITD |  | Medium |  | Q3 2026
8 | Technology Refresh :MS SQL upgrade for ECITS system | Planned | MS SQL upgrade for ECITS system (Support) | afif | IT/COD |  | High |  | Q3 2026
9 | Technology Refresh :MS SQL upgrade for ECR system | Planned | MS SQL upgrade for ECR system (Support) | rozaimi | IT/COD |  | High |  | Q3 2026
10 | Power BI - Monthly Reporting of Trade Finance (EXCO - other matter) | Completed | Dashboard & Reporting | Syahid | COD |  | Medium |  | Q2 2026
11 | Power BI - Monthly Reporting of Non Trade Finance (EXCO - other matter) | Completed | Dashboard & Reporting | Syahid | COD |  | Medium |  | Q2 2026
12 | EFMS - Digitilise Pantry Request Form | Planned | Digitilise Pantry Request Form (WorkFlow) | afif | Admin |  | Medium |  | Q3 2026
13 | efms - Digitilise Stationary Request Form | Completed | Digitilise Stationary Request Form (WorkFlow) | afif | Admin |  | Medium |  | Q2 2026
14 | ECITS - Enhancement : Apprroval Process Digitilization | Planned | Digitilise Approval Process in System | awang | Banking |  | High |  | Q4 2026
15 | MIS - Automation for Credit Limit – Connected Party Transaction | Planned | Reporting | afif | Risk |  | Medium |  | Q2 2026
16 | MIS - Trade Customer Monthly Statement | Planned | Automate Trade Monthly Statement | alifah | COD |  | High
17 | ECR - new reminder redemption report sent to email for ECR bank on maturity date | Completed | Automate Submit reminder to ECR bank on the Bills Maturity | rozaimi | COD |  | High |  | Q3 2026
18 | In-House Microsoft 365 Compliant Passwordless Login | Planned | Enable sso login with device's pin code | rozaimi | IT |  | Medium
19 | Python - CCRIS Template Download | Completed |  | Syahid | Finance |  | Medium |  | Q3 2026
20 | ECITS Enhancement- Go Export Subsidies | Planned | New requirment to enhance policy premium with Go Export Subsidies | awang | Banking |  | High |  | Q3 2026
21 | EFMS - Document Box Tracker | Planned | Digitilise Admin Document Movement (Workflow) | awang | Admin |  | Medium |  | Q4 2026
22 | Power BI - Business Performance | Planned | Dashboard & Reporting | Syahid | Banking |  | Medium |  | Q3 2026
23 | Power BI - Product Profitability | Planned | Dashboard & Reporting | Syahid | Product |  | Medium |  | Q3 2026
24 | Centralized CIF : ECITS integration with Core Banking | Planned | to Centralize CIF module at Core Banking system | afif | ALL |  | High |  | Q4 2026
25 | Centralized CIF : ECR integration with Core Banking | Planned | to Centralize CIF module at Core Banking system | rozaimi | ALL |  | High |  | Q4 2026
26 | Machine Learning Application (Regression) | Planned | Mathematical modelling in prediction requirement for the desired outcome | Syahid | ITD |  | Medium |  | Q4 2026
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From the business perspective

## SME
2026 SME - Innovation & Digital Initiatives List
Initiatives ID | Initiative Name | Status (Completed / In Progress / Not Started) | Description of Initiative | Requester | PIC | Stakeholder | Target Start | Actual Start | Target End | Actual End | Complexity (High/Medium/Low) | Prioritisation (High/Medium/Low) | Budget | Progress | Group | Remarks (Description of Status/RAID)
IDS001 | Unified Data Platform | In Progress | Data driven financing pipeline, Unified DW/DM | CEDAR, SME Bank (SDS) | Azil | CEDAR, SME Bank (SDS) | 2026-01-01 |  | 2026-12-01 |  | High | High |  |  | SME
IDS002 | ELSA Enhancement | In Progress | ELSA apps enhancement | CEDAR, SME Bank (SDS) | Azil | CEDAR, SME Bank (SDS) | 2026-01-01 |  | 2026-12-01 |  | High | High |  |  | SME
IDS003 | Automation Disbursement | In Progress | To accelerate the disbursement process and implement thorough document validation to mitigate fraud risks. | Operation Management | Nadiah, Azil | Operation Management | 2026-01-01 |  | 2026-06-01 |  | Medium | Medium |  |  | SME
IDS004 | Single Point of Truth (SPOT) | In Progress | SPOT as strategic tool by SME Bank to accelerate vetting, enhance risk assessment, and improve customer experience. | Business | Nadiah, Azil | Business | 2026-05-01 |  | 2026-12-01 |  | Medium | Medium |  |  | SME
IDS005 | Techpedia 4.0 | In Progress | The project enhances the existing Techpedia system with Project Mapping, Online Technical Request, and Financial Dashboard modules to improve monitoring, digital processes, reporting, and operational efficiency. | Credit | Faiz, Asyraf, Danisha | Credit | 2026-05-01 |  | 2026-10-01 |  | Medium | Medium |  |  | SME | Development Stage
IDS006 | VAPT Tracker | In Progress | The VAPT Tracking System is a web-based platform to automate VAPT findings tracking, remediation monitoring, notifications, and reporting. The system improves monitoring efficiency, stakeholder visibility, and security governance through centralized management and secure access controls. | IT Security | Faiz, Asyraf, Danisha | IT Security | 2026-05-01 |  | 2026-10-01 |  | Medium | Medium |  |  | SME | Development Stage
IDS007 | Regional Buyer Database System | In Progress | The RENA Buyer Registration & Matching System (BRS) is a web-based system that automates buyer registration, property matching, and notification to agents based on buyer preferences. | SME Bank - RAM | Faiz, Asyraf, Danisha | SME Bank - RAM | 2026-05-01 |  | 2026-10-01 |  | Medium | Medium |  |  | SME | Development Stage
IDS008 | Digitized Tender Evaluation | In Progress | The Tender Evaluation System is a secure digital platform to replace manual Excel-based tender evaluations. The system automates score calculations, standardises scoring, controls user access, maintains audit trails, and improves accuracy, transparency, and procurement governance. | Procurement | Faiz, Asyraf, Danisha | Procurement | 2026-05-01 |  | 2026-10-01 |  | Medium | Medium |  |  | SME | Development Stage
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Function Owner
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on business perspectives

## Phases
Group BPMB - Innovation & Digital Initiatives List
Initiatives ID | Phases | Target Start | Target End | Actual Start | Actual End | Status
IDG001 | 01 - Initiation & Requirements | 2026-01-01 | 2026-01-31 | 2026-01-01 | 2026-01-31
IDG001 | 02 - Assessment | 2026-01-01 | 2026-01-31 | 2026-01-01 | 2026-01-31
IDG001 | 03 - Design & Development | 2026-02-01 | 2026-06-30 | 2026-02-01 | 2026-06-30
IDG001 | 04 - SIT | 2026-07-01 | 2026-09-30 | 2026-07-01
IDG001 | 05 - UAT | 2026-10-01 | 2026-10-31
IDG001 | 06 - Deployment | 2026-11-01 | 2026-11-30
IDG001 | 07 - Hypercare | 2026-12-01 | 2026-12-31
IDG002 | 01 - Initiation & Requirements | 2026-01-01 | 2026-01-31 | 2026-01-01 | 2026-01-31
IDG002 | 02 - Assessment | 2026-01-01 | 2026-01-31 | 2026-01-01 | 2026-01-31
IDG002 | 03 - Design & Development | 2026-02-01 | 2026-06-30 | 2026-02-01 | 2026-06-30
IDG002 | 04 - SIT | 2026-07-01 | 2026-09-30 | 2026-07-01
IDG002 | 05 - UAT | 2026-10-01 | 2026-10-31
IDG002 | 06 - Deployment | 2026-11-01 | 2026-11-30
IDG002 | 07 - Hypercare | 2026-12-01 | 2026-12-31
IDG003 | 01 - Initiation & Requirements | 2026-01-01 | 2026-01-31 | 2026-01-01 | 2026-01-31
IDG003 | 02 - Assessment | 2026-01-01 | 2026-01-31 | 2026-01-01 | 2026-01-31
IDG003 | 03 - Design & Development | 2026-02-01 | 2026-06-30 | 2026-02-01 | 2026-06-30
IDG003 | 04 - SIT | 2026-07-01 | 2026-09-30 | 2026-07-01
IDG003 | 05 - UAT | 2026-10-01 | 2026-10-31
IDG003 | 06 - Deployment | 2026-11-01 | 2026-11-30
IDG003 | 07 - Hypercare | 2026-12-01 | 2026-12-31
IDG004 | 01 - Initiation & Requirements | 2026-08-01 | 2026-08-31 | 2026-08-01
IDG004 | 02 - Assessment | 2026-08-01 | 2026-08-31 | 2026-08-01
IDG004 | 03 - Design & Development | 2026-09-01 | 2026-10-31
IDG004 | 04 - SIT | 2026-11-01 | 2026-11-12
IDG004 | 05 - UAT | 2026-11-13 | 2026-11-30
IDG004 | 06 - Deployment | 2026-12-01 | 2026-12-12
IDG004 | 07 - Hypercare | 2026-12-13 | 2026-12-31
IDG005 | 01 - Initiation & Requirements | 2026-01-01 | 2026-01-31 | 2026-01-01 | 2026-01-31
IDG005 | 02 - Assessment | 2026-01-01 | 2026-01-31 | 2026-01-01 | 2026-01-31
IDG005 | 03 - Design & Development | 2026-02-01 | 2026-06-30 | 2026-02-01 | 2026-06-30
IDG005 | 04 - SIT | 2026-07-01 | 2026-09-30 | 2026-07-01
IDG005 | 05 - UAT | 2026-10-01 | 2026-10-31
IDG005 | 06 - Deployment | 2026-11-01 | 2026-11-30
IDG005 | 07 - Hypercare | 2026-12-01 | 2026-12-31
IDG006 | 01 - Initiation & Requirements | 2026-05-02 | 2026-05-31 | 2026-05-02 | 2026-05-31
IDG006 | 02 - Assessment | 2026-05-02 | 2026-05-31 | 2026-05-02 | 2026-05-31
IDG006 | 03 - Design & Development | 2026-06-01 | 2026-07-31 | 2026-06-01 | 2026-07-31
IDG006 | 04 - SIT | 2026-08-01 | 2026-08-14 | 2026-08-01 | 2026-08-14
IDG006 | 05 - UAT | 2026-08-15 | 2026-08-31 | 2026-08-15
IDG006 | 06 - Deployment | 2026-09-01 | 2026-09-30
IDG006 | 07 - Hypercare | 2026-10-01 | 2026-10-31
IDG007 | 01 - Initiation & Requirements | 2026-07-01 | 2026-07-31 | 2026-07-01 | 2026-07-31
IDG007 | 02 - Assessment | 2026-07-01 | 2026-07-31 | 2026-07-01 | 2026-07-31
IDG007 | 03 - Design & Development | 2026-08-01 | 2026-09-30 | 2026-08-01
IDG007 | 04 - SIT | 2026-10-01 | 2026-10-14
IDG007 | 05 - UAT | 2026-10-15 | 2026-10-30
IDG007 | 06 - Deployment | 2026-11-01 | 2026-11-30
IDG007 | 07 - Hypercare | 2026-12-01 | 2026-12-31
IDG008 | 01 - Initiation & Requirements | 2026-05-02 | 2026-05-31 | 2026-05-02 | 2026-05-31
IDG008 | 02 - Assessment | 2026-05-02 | 2026-05-31 | 2026-05-02 | 2026-05-31
IDG008 | 03 - Design & Development | 2026-06-01 | 2026-08-31 | 2026-06-01 | 2026-08-31
IDG008 | 04 - SIT | 2026-09-01 | 2026-09-30
IDG008 | 05 - UAT | 2026-10-01 | 2026-10-31
IDG008 | 06 - Deployment | 2026-11-01 | 2026-11-30
IDG008 | 07 - Hypercare | 2026-12-01 | 2026-12-31
IDB001 | 01 - Initiation & Requirements | 2026-01-01 | 2026-01-31 | 2025-12-15 | 2026-01-05
IDB001 | 02 - Assessment | 2026-01-15 | 2026-02-15 | 2026-01-02 | 2026-01-12
IDB001 | 03 - Design & Development | 2026-02-01 | 2026-02-28 | 2026-01-13 | 2026-02-05
IDB001 | 04 - SIT | 2026-02-15 | 2026-03-10 | 2026-02-06 | 2026-02-15
IDB001 | 05 - UAT | 2026-03-01 | 2026-03-20 | 2026-02-16 | 2026-02-25
IDB001 | 06 - Deployment | 2026-03-15 | 2026-03-25 | 2026-02-26 | 2026-03-05
IDB001 | 07 - Hypercare | 2026-03-20 | 2026-03-31 | 2026-03-06 | 2026-03-20
IDB002 | 01 - Initiation & Requirements | 2026-01-01 | 2026-01-31 | 2026-01-05 | 2026-01-20
IDB002 | 02 - Assessment | 2026-01-15 | 2026-02-15 | 2026-01-15 | 2026-01-31
IDB002 | 03 - Design & Development | 2026-02-01 | 2026-02-28 | 2026-02-01 | 2026-02-15
IDB002 | 04 - SIT | 2026-02-15 | 2026-03-10 | 2026-02-16 | 2026-02-22
IDB002 | 05 - UAT | 2026-03-01 | 2026-03-20 | 2026-02-23 | 2026-02-28
IDB002 | 06 - Deployment | 2026-03-15 | 2026-03-25 | 2026-03-01 | 2026-03-05
IDB002 | 07 - Hypercare | 2026-03-20 | 2026-03-31 | 2026-03-06 | 2026-03-10
IDB003 | 01 - Initiation & Requirements | 2026-02-01 | 2026-02-28
IDB003 | 02 - Assessment | 2026-02-15 | 2026-03-31
IDB003 | 03 - Design & Development | 2026-03-01 | 2026-04-30
IDB003 | 04 - SIT | 2026-04-15 | 2026-05-15
IDB003 | 05 - UAT | 2026-05-01 | 2026-05-31
IDB003 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDB003 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDB004 | 01 - Initiation & Requirements | 2026-02-01 | 2026-02-28
IDB004 | 02 - Assessment | 2026-02-15 | 2026-03-31
IDB004 | 03 - Design & Development | 2026-03-01 | 2026-04-30
IDB004 | 04 - SIT | 2026-04-15 | 2026-05-15
IDB004 | 05 - UAT | 2026-05-01 | 2026-05-31
IDB004 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDB004 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDB005 | 01 - Initiation & Requirements | 2026-02-01 | 2026-02-28
IDB005 | 02 - Assessment | 2026-02-15 | 2026-03-31
IDB005 | 03 - Design & Development | 2026-03-01 | 2026-04-30
IDB005 | 04 - SIT | 2026-04-15 | 2026-05-15
IDB005 | 05 - UAT | 2026-05-01 | 2026-05-31
IDB005 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDB005 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDB006 | 01 - Initiation & Requirements | 2026-06-01 | 2026-06-30 | 2026-04-10 | 2026-04-30
IDB006 | 02 - Assessment | 2026-06-15 | 2026-07-15 | 2026-05-01 | 2026-05-15
IDB006 | 03 - Design & Development | 2026-07-01 | 2026-08-15 | 2026-05-16 | 2026-06-30
IDB006 | 04 - SIT | 2026-08-01 | 2026-08-15 | 2026-07-01 | 2026-07-15
IDB006 | 05 - UAT | 2026-08-16 | 2026-08-30 | 2026-07-16 | 2026-07-31
IDB006 | 06 - Deployment | 2026-09-01 | 2026-09-15 | 2026-08-01 | 2026-08-10
IDB006 | 07 - Hypercare | 2026-09-16 | 2026-09-30 | 2026-08-11
IDB007 | 01 - Initiation & Requirements | 2026-06-01 | 2026-06-30
IDB007 | 02 - Assessment | 2026-06-15 | 2026-07-15
IDB007 | 03 - Design & Development | 2026-07-01 | 2026-08-15
IDB007 | 04 - SIT | 2026-08-01 | 2026-08-15
IDB007 | 05 - UAT | 2026-08-16 | 2026-08-30
IDB007 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDB007 | 07 - Hypercare | 2026-09-16 | 2026-09-30
IDB008 | 01 - Initiation & Requirements | 2026-06-01 | 2026-06-30
IDB008 | 02 - Assessment | 2026-06-15 | 2026-07-15
IDB008 | 03 - Design & Development | 2026-07-01 | 2026-08-15
IDB008 | 04 - SIT | 2026-08-01 | 2026-08-15
IDB008 | 05 - UAT | 2026-08-16 | 2026-08-30
IDB008 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDB008 | 07 - Hypercare | 2026-09-16 | 2026-09-30
IDB009 | 01 - Initiation & Requirements | 2026-09-01 | 2026-09-30
IDB009 | 02 - Assessment | 2026-09-15 | 2026-10-15
IDB009 | 03 - Design & Development | 2026-10-01 | 2026-11-15
IDB009 | 04 - SIT | 2026-11-01 | 2026-11-15
IDB009 | 05 - UAT | 2026-11-16 | 2026-11-30
IDB009 | 06 - Deployment | 2026-12-01 | 2026-12-15
IDB009 | 07 - Hypercare | 2026-12-16 | 2026-12-31
IDB010 | 01 - Initiation & Requirements | 2026-02-01 | 2026-02-28
IDB010 | 02 - Assessment | 2026-02-15 | 2026-03-31
IDB010 | 03 - Design & Development | 2026-03-01 | 2026-04-30
IDB010 | 04 - SIT | 2026-04-15 | 2026-05-15
IDB010 | 05 - UAT | 2026-05-01 | 2026-05-31
IDB010 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDB010 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDB011 | 01 - Initiation & Requirements | 2026-01-01 | 2026-01-31 | 2026-01-05 | 2026-01-20
IDB011 | 02 - Assessment | 2026-01-15 | 2026-02-15 | 2026-01-21 | 2026-02-05
IDB011 | 03 - Design & Development | 2026-02-01 | 2026-04-30 | 2026-02-06 | 2026-04-15
IDB011 | 04 - SIT | 2026-04-15 | 2026-05-15
IDB011 | 05 - UAT | 2026-05-01 | 2026-05-31
IDB011 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDB011 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDB012 | 01 - Initiation & Requirements | 2026-01-01 | 2026-01-31 | 2026-01-05 | 2026-01-20
IDB012 | 02 - Assessment | 2026-01-15 | 2026-02-15 | 2026-01-21 | 2026-02-05
IDB012 | 03 - Design & Development | 2026-02-01 | 2026-04-30 | 2026-02-06 | 2026-04-15
IDB012 | 04 - SIT | 2026-04-15 | 2026-05-15 | 2026-04-16 | 2026-04-30
IDB012 | 05 - UAT | 2026-05-01 | 2026-05-31 | 2026-05-01 | 2026-05-31
IDB012 | 06 - Deployment | 2026-06-01 | 2026-06-15 | 2026-06-01 | 2026-09-10
IDB012 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDB013 | 01 - Initiation & Requirements | 2026-02-01 | 2026-02-28 | 2026-03-10 | 2026-03-20
IDB013 | 02 - Assessment | 2026-02-15 | 2026-03-31 | 2026-03-21 | 2026-03-31
IDB013 | 03 - Design & Development | 2026-03-01 | 2026-04-30 | 2026-04-01 | 2026-04-30
IDB013 | 04 - SIT | 2026-04-15 | 2026-05-15 | 2026-05-01 | 2026-05-15
IDB013 | 05 - UAT | 2026-05-01 | 2026-05-31 | 2026-05-16 | 2026-05-31
IDB013 | 06 - Deployment | 2026-06-01 | 2026-06-15 | 2026-06-01 | 2026-06-10
IDB013 | 07 - Hypercare | 2026-06-16 | 2026-06-30 | 2026-06-11 | 2026-06-30
IDB014 | 01 - Initiation & Requirements | 2026-06-01 | 2026-06-30
IDB014 | 02 - Assessment | 2026-06-15 | 2026-07-15
IDB014 | 03 - Design & Development | 2026-07-01 | 2026-08-15
IDB014 | 04 - SIT | 2026-08-01 | 2026-08-15
IDB014 | 05 - UAT | 2026-08-16 | 2026-08-30
IDB014 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDB014 | 07 - Hypercare | 2026-09-16 | 2026-09-30
IDB015 | 01 - Initiation & Requirements | 2026-02-01 | 2026-02-28
IDB015 | 02 - Assessment | 2026-02-15 | 2026-03-31
IDB015 | 03 - Design & Development | 2026-03-01 | 2026-04-30
IDB015 | 04 - SIT | 2026-04-15 | 2026-05-15
IDB015 | 05 - UAT | 2026-05-01 | 2026-05-31
IDB015 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDB015 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDB016 | 01 - Initiation & Requirements | 2026-09-01 | 2026-09-30
IDB016 | 02 - Assessment | 2026-09-15 | 2026-10-15
IDB016 | 03 - Design & Development | 2026-10-01 | 2026-11-15
IDB016 | 04 - SIT | 2026-11-01 | 2026-11-15
IDB016 | 05 - UAT | 2026-11-16 | 2026-11-30
IDB016 | 06 - Deployment | 2026-12-01 | 2026-12-15
IDB016 | 07 - Hypercare | 2026-12-16 | 2026-12-31
IDB017 | 01 - Initiation & Requirements | 2025-11-01 | 2025-11-30 | 2025-11-10 | 2025-11-20
IDB017 | 02 - Assessment | 2025-11-15 | 2025-12-31 | 2025-11-21 | 2025-12-10
IDB017 | 03 - Design & Development | 2025-12-01 | 2026-01-31 | 2025-12-11 | 2026-01-31
IDB017 | 04 - SIT | 2026-01-15 | 2026-02-15 | 2026-02-01 | 2026-02-15
IDB017 | 05 - UAT | 2026-02-01 | 2026-02-28 | 2026-02-16 | 2026-02-28
IDB017 | 06 - Deployment | 2026-03-01 | 2026-03-15 | 2026-03-01 | 2026-03-10
IDB017 | 07 - Hypercare | 2026-03-16 | 2026-03-31 | 2026-03-11 | 2026-03-25
IDB018 | 01 - Initiation & Requirements | 2026-06-01 | 2026-06-30
IDB018 | 02 - Assessment | 2026-06-15 | 2026-07-15
IDB018 | 03 - Design & Development | 2026-07-01 | 2026-08-15
IDB018 | 04 - SIT | 2026-08-01 | 2026-08-15
IDB018 | 05 - UAT | 2026-08-16 | 2026-08-30
IDB018 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDB018 | 07 - Hypercare | 2026-09-16 | 2026-09-30
IDB019 | 01 - Initiation & Requirements | 2026-06-01 | 2026-06-30
IDB019 | 02 - Assessment | 2026-06-15 | 2026-07-15
IDB019 | 03 - Design & Development | 2026-07-01 | 2026-08-15
IDB019 | 04 - SIT | 2026-08-01 | 2026-08-15
IDB019 | 05 - UAT | 2026-08-16 | 2026-08-30
IDB019 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDB019 | 07 - Hypercare | 2026-09-16 | 2026-09-30
IDE001 | 01 - Initiation & Requirements | 2026-09-01 | 2026-09-15
IDE001 | 02 - Assessment | 2026-09-10 | 2026-09-30
IDE001 | 03 - Design & Development | 2026-10-01 | 2026-10-31
IDE001 | 04 - SIT | 2026-10-20 | 2026-11-10
IDE001 | 05 - UAT | 2026-11-01 | 2026-11-20
IDE001 | 06 - Deployment | 2026-11-21 | 2026-12-10
IDE001 | 07 - Hypercare | 2026-12-11 | 2026-12-31
IDE002 | 01 - Initiation & Requirements | 2026-09-01 | 2026-09-15
IDE002 | 02 - Assessment | 2026-09-10 | 2026-09-30
IDE002 | 03 - Design & Development | 2026-10-01 | 2026-10-31
IDE002 | 04 - SIT | 2026-10-20 | 2026-11-10
IDE002 | 05 - UAT | 2026-11-01 | 2026-11-20
IDE002 | 06 - Deployment | 2026-11-21 | 2026-12-10
IDE002 | 07 - Hypercare | 2026-12-11 | 2026-12-31
IDE003 | 01 - Initiation & Requirements | 2026-03-01 | 2026-03-15
IDE003 | 02 - Assessment | 2026-03-10 | 2026-03-31
IDE003 | 03 - Design & Development | 2026-04-01 | 2026-04-30
IDE003 | 04 - SIT | 2026-04-15 | 2026-05-15
IDE003 | 05 - UAT | 2026-05-01 | 2026-05-31
IDE003 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDE003 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDE004 | 01 - Initiation & Requirements | 2026-03-01 | 2026-03-15
IDE004 | 02 - Assessment | 2026-03-10 | 2026-03-31
IDE004 | 03 - Design & Development | 2026-04-01 | 2026-04-30
IDE004 | 04 - SIT | 2026-04-15 | 2026-05-15
IDE004 | 05 - UAT | 2026-05-01 | 2026-05-31
IDE004 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDE004 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDE005 | 01 - Initiation & Requirements | 2026-03-01 | 2026-03-15
IDE005 | 02 - Assessment | 2026-03-10 | 2026-03-31
IDE005 | 03 - Design & Development | 2026-04-01 | 2026-04-30
IDE005 | 04 - SIT | 2026-04-15 | 2026-05-15
IDE005 | 05 - UAT | 2026-05-01 | 2026-05-31
IDE005 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDE005 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDE006 | 01 - Initiation & Requirements | 2026-03-01 | 2026-03-15
IDE006 | 02 - Assessment | 2026-03-10 | 2026-03-31
IDE006 | 03 - Design & Development | 2026-04-01 | 2026-04-30
IDE006 | 04 - SIT | 2026-04-15 | 2026-05-15
IDE006 | 05 - UAT | 2026-05-01 | 2026-05-31
IDE006 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDE006 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDE007 | 01 - Initiation & Requirements | 2026-06-01 | 2026-06-15
IDE007 | 02 - Assessment | 2026-06-10 | 2026-06-30
IDE007 | 03 - Design & Development | 2026-07-01 | 2026-07-31
IDE007 | 04 - SIT | 2026-07-15 | 2026-07-31
IDE007 | 05 - UAT | 2026-08-01 | 2026-08-31
IDE007 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDE007 | 07 - Hypercare | 2026-09-16 | 2026-09-30
IDE008 | 01 - Initiation & Requirements | 2026-06-01 | 2026-06-15
IDE008 | 02 - Assessment | 2026-06-10 | 2026-06-30
IDE008 | 03 - Design & Development | 2026-07-01 | 2026-07-31
IDE008 | 04 - SIT | 2026-07-15 | 2026-07-31
IDE008 | 05 - UAT | 2026-08-01 | 2026-08-31
IDE008 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDE008 | 07 - Hypercare | 2026-09-16 | 2026-09-30
IDE009 | 01 - Initiation & Requirements | 2026-06-01 | 2026-06-15
IDE009 | 02 - Assessment | 2026-06-10 | 2026-06-30
IDE009 | 03 - Design & Development | 2026-07-01 | 2026-07-31
IDE009 | 04 - SIT | 2026-07-15 | 2026-07-31
IDE009 | 05 - UAT | 2026-08-01 | 2026-08-31
IDE009 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDE009 | 07 - Hypercare | 2026-09-16 | 2026-09-30
IDE010 | 01 - Initiation & Requirements | 2026-03-01 | 2026-03-15
IDE010 | 02 - Assessment | 2026-03-10 | 2026-03-31
IDE010 | 03 - Design & Development | 2026-04-01 | 2026-04-30
IDE010 | 04 - SIT | 2026-04-15 | 2026-05-15
IDE010 | 05 - UAT | 2026-05-01 | 2026-05-31
IDE010 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDE010 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDE011 | 01 - Initiation & Requirements | 2026-03-01 | 2026-03-15
IDE011 | 02 - Assessment | 2026-03-10 | 2026-03-31
IDE011 | 03 - Design & Development | 2026-04-01 | 2026-04-30
IDE011 | 04 - SIT | 2026-04-15 | 2026-05-15
IDE011 | 05 - UAT | 2026-05-01 | 2026-05-31
IDE011 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDE011 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDE012 | 01 - Initiation & Requirements | 2026-06-01 | 2026-06-15
IDE012 | 02 - Assessment | 2026-06-10 | 2026-06-30
IDE012 | 03 - Design & Development | 2026-07-01 | 2026-07-31
IDE012 | 04 - SIT | 2026-07-15 | 2026-07-31
IDE012 | 05 - UAT | 2026-08-01 | 2026-08-31
IDE012 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDE012 | 07 - Hypercare | 2026-09-16 | 2026-09-30
IDE013 | 01 - Initiation & Requirements | 2026-03-01 | 2026-03-15
IDE013 | 02 - Assessment | 2026-03-10 | 2026-03-31
IDE013 | 03 - Design & Development | 2026-04-01 | 2026-04-30
IDE013 | 04 - SIT | 2026-04-15 | 2026-05-15
IDE013 | 05 - UAT | 2026-05-01 | 2026-05-31
IDE013 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDE013 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDE014 | 01 - Initiation & Requirements | 2026-09-01 | 2026-09-15
IDE014 | 02 - Assessment | 2026-09-10 | 2026-09-30
IDE014 | 03 - Design & Development | 2026-10-01 | 2026-10-31
IDE014 | 04 - SIT | 2026-10-20 | 2026-11-10
IDE014 | 05 - UAT | 2026-11-01 | 2026-11-20
IDE014 | 06 - Deployment | 2026-11-21 | 2026-12-10
IDE014 | 07 - Hypercare | 2026-12-11 | 2026-12-31
IDE015 | 01 - Initiation & Requirements | 2026-03-01 | 2026-03-15
IDE015 | 02 - Assessment | 2026-03-10 | 2026-03-31
IDE015 | 03 - Design & Development | 2026-04-01 | 2026-04-30
IDE015 | 04 - SIT | 2026-04-15 | 2026-05-15
IDE015 | 05 - UAT | 2026-05-01 | 2026-05-31
IDE015 | 06 - Deployment | 2026-06-01 | 2026-06-15
IDE015 | 07 - Hypercare | 2026-06-16 | 2026-06-30
IDE016 | 01 - Initiation & Requirements
IDE016 | 02 - Assessment
IDE016 | 03 - Design & Development
IDE016 | 04 - SIT
IDE016 | 05 - UAT
IDE016 | 06 - Deployment
IDE016 | 07 - Hypercare
IDE017 | 01 - Initiation & Requirements | 2026-06-01 | 2026-06-15
IDE017 | 02 - Assessment | 2026-06-10 | 2026-06-30
IDE017 | 03 - Design & Development | 2026-07-01 | 2026-07-31
IDE017 | 04 - SIT | 2026-07-15 | 2026-07-31
IDE017 | 05 - UAT | 2026-08-01 | 2026-08-31
IDE017 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDE017 | 07 - Hypercare | 2026-09-16 | 2026-09-30
IDE018 | 01 - Initiation & Requirements
IDE018 | 02 - Assessment
IDE018 | 03 - Design & Development
IDE018 | 04 - SIT
IDE018 | 05 - UAT
IDE018 | 06 - Deployment
IDE018 | 07 - Hypercare
IDE019 | 01 - Initiation & Requirements
IDE019 | 02 - Assessment
IDE019 | 03 - Design & Development
IDE019 | 04 - SIT
IDE019 | 05 - UAT
IDE019 | 06 - Deployment
IDE019 | 07 - Hypercare
IDE020 | 01 - Initiation & Requirements | 2026-06-01 | 2026-06-15
IDE020 | 02 - Assessment | 2026-06-10 | 2026-06-30
IDE020 | 03 - Design & Development | 2026-07-01 | 2026-07-31
IDE020 | 04 - SIT | 2026-07-15 | 2026-07-31
IDE020 | 05 - UAT | 2026-08-01 | 2026-08-31
IDE020 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDE020 | 07 - Hypercare | 2026-09-16 | 2026-09-30
IDE021 | 01 - Initiation & Requirements | 2026-09-01 | 2026-09-15
IDE021 | 02 - Assessment | 2026-09-10 | 2026-09-30
IDE021 | 03 - Design & Development | 2026-10-01 | 2026-10-31
IDE021 | 04 - SIT | 2026-10-20 | 2026-11-10
IDE021 | 05 - UAT | 2026-11-01 | 2026-11-20
IDE021 | 06 - Deployment | 2026-11-21 | 2026-12-10
IDE021 | 07 - Hypercare | 2026-12-11 | 2026-12-31
IDE022 | 01 - Initiation & Requirements | 2026-06-01 | 2026-06-15
IDE022 | 02 - Assessment | 2026-06-10 | 2026-06-30
IDE022 | 03 - Design & Development | 2026-07-01 | 2026-07-31
IDE022 | 04 - SIT | 2026-07-15 | 2026-07-31
IDE022 | 05 - UAT | 2026-08-01 | 2026-08-31
IDE022 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDE022 | 07 - Hypercare | 2026-09-16 | 2026-09-30
IDE023 | 01 - Initiation & Requirements
IDE023 | 02 - Assessment
IDE023 | 03 - Design & Development
IDE023 | 04 - SIT
IDE023 | 05 - UAT
IDE023 | 06 - Deployment
IDE023 | 07 - Hypercare
IDE024 | 01 - Initiation & Requirements | 2026-09-01 | 2026-09-15
IDE024 | 02 - Assessment | 2026-09-10 | 2026-09-30
IDE024 | 03 - Design & Development | 2026-10-01 | 2026-10-31
IDE024 | 04 - SIT | 2026-10-20 | 2026-11-10
IDE024 | 05 - UAT | 2026-11-01 | 2026-11-20
IDE024 | 06 - Deployment | 2026-11-21 | 2026-12-10
IDE024 | 07 - Hypercare | 2026-12-11 | 2026-12-31
IDE025 | 01 - Initiation & Requirements | 2026-09-01 | 2026-09-15
IDE025 | 02 - Assessment | 2026-09-10 | 2026-09-30
IDE025 | 03 - Design & Development | 2026-10-01 | 2026-10-31
IDE025 | 04 - SIT | 2026-10-20 | 2026-11-10
IDE025 | 05 - UAT | 2026-11-01 | 2026-11-20
IDE025 | 06 - Deployment | 2026-11-21 | 2026-12-10
IDE025 | 07 - Hypercare | 2026-12-11 | 2026-12-31
IDE026 | 01 - Initiation & Requirements | 2026-09-01 | 2026-09-15
IDE026 | 02 - Assessment | 2026-09-10 | 2026-09-30
IDE026 | 03 - Design & Development | 2026-10-01 | 2026-10-31
IDE026 | 04 - SIT | 2026-10-20 | 2026-11-10
IDE026 | 05 - UAT | 2026-11-01 | 2026-11-20
IDE026 | 06 - Deployment | 2026-11-21 | 2026-12-10
IDE026 | 07 - Hypercare | 2026-12-11 | 2026-12-31
IDS001 | 01 - Initiation & Requirements | 2026-01-01 | 2026-01-31
IDS001 | 02 - Assessment | 2026-01-15 | 2026-02-28
IDS001 | 03 - Design & Development | 2026-03-01 | 2026-05-31
IDS001 | 04 - SIT | 2026-06-01 | 2026-06-30
IDS001 | 05 - UAT | 2026-07-01 | 2026-07-31
IDS001 | 06 - Deployment | 2026-08-01 | 2026-08-31
IDS001 | 07 - Hypercare | 2026-09-01 | 2026-12-31
IDS002 | 01 - Initiation & Requirements | 2026-01-01 | 2026-01-31
IDS002 | 02 - Assessment | 2026-01-15 | 2026-02-28
IDS002 | 03 - Design & Development | 2026-03-01 | 2026-05-31
IDS002 | 04 - SIT | 2026-06-01 | 2026-06-30
IDS002 | 05 - UAT | 2026-07-01 | 2026-07-31
IDS002 | 06 - Deployment | 2026-08-01 | 2026-08-31
IDS002 | 07 - Hypercare | 2026-09-01 | 2026-12-31
IDS003 | 01 - Initiation & Requirements | 2026-01-01 | 2026-01-31
IDS003 | 02 - Assessment | 2026-01-15 | 2026-02-15
IDS003 | 03 - Design & Development | 2026-02-01 | 2026-03-31
IDS003 | 04 - SIT | 2026-03-15 | 2026-04-15
IDS003 | 05 - UAT | 2026-04-01 | 2026-04-30
IDS003 | 06 - Deployment | 2026-05-01 | 2026-05-31
IDS003 | 07 - Hypercare | 2026-06-01 | 2026-06-30
IDS004 | 01 - Initiation & Requirements | 2026-05-01 | 2026-05-31
IDS004 | 02 - Assessment | 2026-05-15 | 2026-06-15
IDS004 | 03 - Design & Development | 2026-06-01 | 2026-07-31
IDS004 | 04 - SIT | 2026-07-15 | 2026-07-31
IDS004 | 05 - UAT | 2026-08-01 | 2026-08-31
IDS004 | 06 - Deployment | 2026-09-01 | 2026-09-30
IDS004 | 07 - Hypercare | 2026-10-01 | 2026-12-31
IDS005 | 01 - Initiation & Requirements | 2026-05-01 | 2026-05-31
IDS005 | 02 - Assessment | 2026-05-15 | 2026-06-15
IDS005 | 03 - Design & Development | 2026-06-01 | 2026-07-31
IDS005 | 04 - SIT | 2026-07-15 | 2026-07-31
IDS005 | 05 - UAT | 2026-08-01 | 2026-08-31
IDS005 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDS005 | 07 - Hypercare | 2026-09-16 | 2026-10-31
IDS006 | 01 - Initiation & Requirements | 2026-05-01 | 2026-05-31
IDS006 | 02 - Assessment | 2026-05-15 | 2026-06-15
IDS006 | 03 - Design & Development | 2026-06-01 | 2026-07-31
IDS006 | 04 - SIT | 2026-07-15 | 2026-07-31
IDS006 | 05 - UAT | 2026-08-01 | 2026-08-31
IDS006 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDS006 | 07 - Hypercare | 2026-09-16 | 2026-10-31
IDS007 | 01 - Initiation & Requirements | 2026-05-01 | 2026-05-31
IDS007 | 02 - Assessment | 2026-05-15 | 2026-06-15
IDS007 | 03 - Design & Development | 2026-06-01 | 2026-07-31
IDS007 | 04 - SIT | 2026-07-15 | 2026-07-31
IDS007 | 05 - UAT | 2026-08-01 | 2026-08-31
IDS007 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDS007 | 07 - Hypercare | 2026-09-16 | 2026-10-31
IDS008 | 01 - Initiation & Requirements | 2026-05-01 | 2026-05-31
IDS008 | 02 - Assessment | 2026-05-15 | 2026-06-15
IDS008 | 03 - Design & Development | 2026-06-01 | 2026-07-31
IDS008 | 04 - SIT | 2026-07-15 | 2026-07-31
IDS008 | 05 - UAT | 2026-08-01 | 2026-08-31
IDS008 | 06 - Deployment | 2026-09-01 | 2026-09-15
IDS008 | 07 - Hypercare | 2026-09-16 | 2026-10-31